## Coversheet
This is a partial GAP work plan example for illustrative purposes only. Grantees should develop work plans in alignment with the GAP Statute, GAP Guidance and their own ETEPs. Use of this example does not guarantee approval or funding amounts.
November, 2020
INDIAN ENVIRONMENTAL
GENERAL ASSISTANCE PROGRAM
REGION 9 COOPERATIVE AGREEMENT RESOURCE SPREADSHEET "GAP WORKBOOK"
Introduction & Instructions
The GAP workbook was co-developed by Tribal environmental and US EPA personel to streamline the co-management of GAP and PPG cooperative agreements in Region 9. Thank you to everyone who contributed. Please follow the short instruction guide below, and reach out to your GAP project officer with any questions. * Please note that all available templates and tools in this workbook are completely optional.
1. Save GAP workbook to your desktop and rename to your liking. After making any changes, remember to "Save As" with your perferred nomenclature and date. That way, you always have an orginal copy saved to your computer as well as any saved modifications. If anything happens to your original copy, download from EPA R9's website or request another one from your Project Officer.
2. Explore workbook by clicking on all visible tabs at bottom. Primary tabs include workplan, budget and progress reporting templates; and tools to generate accurate cost estimates and track deliverables. Right click on any of the active tabs below and then click "unhide" to see a list of all hidden tabs. Simply click on any of the tabs listed to make it active and visible below.
3. Choose a workplan template, a budget template and progress reporting template that you would like to use and delete or hide all other templates/tabs. As above, right clic on any tab below to hide or delete any tabs that you do not need, or rename as needed.
4. Draft GAP workplan activities for upcoming Fiscal Year on chosen template, referencing the Tribe's ETEP to ensure activities support Tribal Environmental Priorities and GAP Guidance to ensure GAP-eligibility. Please include identified priorities, capacity indicators, and timeframe for completion for each activity, but leave the estimated costs and estimated FTE cells blank. Delete any rows that are not in use to consolidate workplan commitments.
5. Use Cost-Estimator Tool to accurately estimate commitment costs and for workplan. You may need to modify the rows to match the workplan and columns to reflect the positions working under the grant. Fill in the auto-fill data at the top with salaries, fringe, and IDC, so you don't have to input this information more than once. If using a template that is pre-formatted to auto-populate, FTE and cost estimates will auto-populate from this tool to the workplan. If you choose a tempate that is not pre-formatted, you can manually add the estimates generated into your workplan.
6. Once the commitment costs estimator has been filled out, use the budget category totals from cost estimator tool to complete the budget detail and the estimated commitment/componet costs and FTE allocation to complete the workplan. If using a pre-formatted template, these totals will autopopulate between tabs. Please confirm that the workplan and budget totals match exactly to the whole dollar amount before sending to EPA for review.
7. EPA will review the draft workplan and budget submitted and can provide comments on the same draft workplan tab if requested. Comments will be provided in the workbook and/or via email or uploaded to a shared One Drive folder.
8. Once the workplan has been finalized and approved, the file will be "Saved As" 'FYXXXX, Tribe's Name, Final Workplan and Budget' by GAP PO and returned to grantee. PDFs can be created by "Saving As" PDF, for printing and/or separate record keeping.
9. With an approved workplan and budget in the spreadsheet, quarterly progress reporting can commence on one of the reporting templates chosen. The reporting templates included in this workbook auto-populate with commitment descriptions and outputs and deliverables for easy reference. You may need to unhide a grouping to make them visible. Please hide any unused rows for conservation of space. Quarterly reporting and EOY joint evaluation process begins with grantee self-evaluation.
10. Consider using the deliverable tracking tool each quarter, to account for all deliverables submitted or not submitted to EPA. The deliverable tracking tool can be linked so that it auto-populates into the EOY Joint Evaluation. The estimated % complete and justified expenditures from deliverables submitted is only a starting point for a more nuanced conversation and robust joint evaluation.
INDEX: Primary Tabs | Excel Shortcut Key (For PC)
Coversheet
FY22 Draft Workplan | Ctrl+Z: Undo an action
FY22 Cost Estimator Tool | Ctrl+Y: Redo an action
FY22 Draft Budget Detail | Tab: Go to the next cell
FY22 Progress Report & EOY | Alt+Enter: Insert a hard return within a cell (while editing a cell)
Ctrl+X: Cut contents of a cell, selected data, or selected cell range
| Ctrl+C or Ctrl+Insert: Copy contents of a cell, selected data, or selected cell range |  | ``
Ctrl+V or Shift+Insert: Paste contents of a cell, selected data, or selected cell range
Additional Tabs | F7: Check spelling
Cumulative Quarterly Report - Simple | Ctrl+F1: Hide or Show ribbon
Alt. Progress & EOY | Ctrl+Up/Down Arrow: Move to the top or bottom cell in the column
Deliverable Status Ex. | Ctrl+F2: Switch to Print Preview |  | ```
Draft Workplan Review (EPA use) | Shift+Tab: Go to the previous cell
Shift+F2: Add or edit a cell comment
ALT+H, then O, then A: Expand cell row to fit text
F12: Open Save As; Ctrl + s; Save existing workbook
Esc: Back out of selected function

## FY22 Draft Workplan
[9 empty] | ^^ Supporting Info Column | [5 empty] | ^^^ EPA Review Comments
This is a partial GAP work plan example for illustrative purposes only. Grantees should develop work plans in alignment with the GAP Statute, GAP Guidance and their own ETEPs. Use of this example does not guarantee approval or funding amounts.
| GENERAL ASSISTANCE PROGRAM | [8 empty] | GENERAL ASSISTANCE PROGRAM
| (TRIBE'S NAME _COOPERATIVE AGREEMENT #_Fiscal Year 20xx_Year #) | [8 empty] | (TRIBE'S NAME _COOPERATIVE AGREEMENT #_Fiscal Year 20xx_Year #)
| ORIGINAL or REVISED WORKPLAN |  |  |  | Date Last Modified: |  | xx/xx/20xx |  |  | EPA Review and Comments to Grantee
<< Display Title | # | Component and Commitment Descriptions | Outputs, Deliverables & Outcomes | Capacity Indicators | Target End Date | Estimated FTE (from cost est.) | Estimated Cost (from cost est.) | Supporting Information |  | Project Officer | Media Specific | EPA Comments | Recommended FTE | Recommended Cost
| 1 | Administration of Environmental Office: | Environmental Outcomes: Compliance with Tribal and EPA administrative requirements and internally coordinated initiatives to improve environmental conditions ETEP Priority: #8 Environmental Office Administration | B.2.2, B2.4, B.3.1, B.4.1, B.6.6 |  | 0.1947 | 25654 |  |  | Tribe's proposal was for 1.486 FTE, basically same as last year. We can go with that (preferred) if funds are available. The final work plan can be adjusted to equal to 1.486 FTE if Tribe and Manager agree with the recommendations below. If sufficient funds are not available, we can scale back as recommended here, as our least preferred option. | 0
| 1.1 | The Director and Manager will administer general aspects of the GAP Grant, which will include but may not be limited to the following: answering phone calls, responding to emails, filing, attending weekly staff meetings, ordering supplies and equipment, adhering to time-keeping processes, paying utility bills, etc. Staff meetings will be held Mondays 8:30 - 9:30 AM. | 4 samples of weekly staff meeting notes and sign in sheets | B.2.2 | Every work week until 9/30/22 | 0.067308 | 11563 |  |  | OK. Equates to 1.15 hours for Dir and 1.9 hrs for Mgr per week for staff meetings and general admin. | 0
| 1.2 | The Manager will prepare quarterly progress reports, submit them to the Director for review and submit final reports to US EPA by: Jan 30, Apr 28, Jul 31, and Oct 31. The Tribe will conduct a Joint Evaluation with US EPA GAP Project Officer. Evaluation elements are: 1. A discussion of accomplishments as measured against workplan commitments. 2. A discussion of cumulative effectiveness of the workplan performed under all workplan components. 3. A discussion of existing and potential problem areas. 4. Schedule discussions (4) with our Project Officer within two weeks of submitting progress reports. The Tribe will review a draft annual report prepared by US EPA and will discuss progress under the grant with US EPA prior to finalization of report. 5. Tribe will submit final evaluation reports to US EPA. | 4 Quarterly Reports | B.2.4 | 01/31/22, 04/28/22, 07/31/22, 10/31/22 | 0.043269 | 4854 |  |  | OK. Dir 6 hrs and mgr 12 hrs each for 5 reports including EOY. Also includes 4 report follow-up meetings. Seems reasonable but maybe a scosh high. | 0
| 1.3 | The Director and Manager will work with the Tribal Accountant 2 times a month to review general ledgers, compare actual expenditures to projected expenditures, determine whether budget modifications are necessary, etc. The Manager will track all expenditures in a cuff-account spreadsheet and compare cuff-account data with the Tribe's offical ledger to help ensure charges to the GAP grant are correct. | 4 line item expenditure reports will be submitted along with EPA progress reports quarterly. | B.3.1 | 01/31/22, 04/28/22, 07/31/22, 10/31/22 | 0.034615 | 3779 |  |  | OK. dir @ 3/qtr and mgr @ 1.25/week to run a cuff account spreadsheet, QA accounting data, meet with accountant seems reasonable. | 0
| 1.4 | The Director and Manager will develop a calendar of upcoming training and events. The NRD and REPA Manager will share a Google Calender of trainings and events. This will help the program run effectively and efficiently and keep the program on track with workplan commitments and deliverables. | 4 samples of monthly calendars | B.4.1 | By 10/15/21 initially and updated at least monthly thereafter | 0.014423 | 1619 |  |  | Ok. mgr abut 23 minutes per week to add entries to calendar and review upcoming events and deadlines. | 0
| 1.5 | The Director and Manager will attend monthly Council meetings on the 2nd Wednesday of each month to inform them of grant progress and environmental issues, and to seek approval of grant budgets, work plans, proposals, applications, purchases, travel, consultation correspondence, etc. | 3 monthly sign-in sheets and meeting notes | B.6.9 | 2nd Wednesday of each month | 0.020192 | 2247 |  |  | OK. Dir 1 and mgr 2.5 hrs for each monthly council meeting. | 0
| 1.6 | The Manager and Director will continue to store and manage environmental and grant documents on the Triba/EPA OneDrive. They will update contacts information and email lists on as additional contacts are developed. | A copy of the contact list and two screen shots of OneDrive directories showing grants and directory structures. | B.6.6 | Routine updates with final deliverables provided nlt 10/31/22 | 0.014904 | 1592 |  |  | OK. dir 1 and mgr 30 hrs/year to manage files on their shared drives and update agency contact lists | 0
| 2 | Travel and Training | Increased knowledge of environmental issues & technical skills. |  |  | 0.0577 | 14182 |  |  | 0 | 0
| 2.1 | The Manager and Director will drive (one vehicle) to San Francisco to attend the 2021 Annual tribal/EPA Conference and companion RTOC meeting in October. | Copies of any conference or RTOC presentations staff may develop and a summary of presentations or events attended. | B.2.2 | 2021-10-31 | 0.038462 | 10740 |  |  | 0 | 0
| 2.2 | The Manager will fly to Reno to attend the 2021 Spring RTOC meeting, which is slated for 03/15/2022. | Copies of any meeting materials the Manager may develop and a summary of sessions attended if applicable. | B.6.7 | 2022-04-01 | 0.019231 | 3442 |  |  | 0 | 0
| 3 | Outreach and Education |  |  |  | 0.024 | 8421 |  |  | 0 | 0
| 3.1 | Staff will plan, conduct and follow-up on one Rancheria cleanup day to celebrate earth day and improve awareness of solid waste issues and solutions. Cleanup activities will be distributed based on the age and physical condtion of participants. Children, elders and other physically compromised individuals will not be exposed to any heavy lifting or unsafe terrain. The goals of the event are to make people aware of illegal dumping and related environmental consequences, demonstrate how individuals can recycle and divert materials from their waste streams, and encourage people to recycle more and refrain from illegal dumping. Staff will develop a safety plan and conduct a safety meeting prior to participants starting the cleanup. All participants will be issued personal protective equipment such as gloves, goggles, hard hats, and face masks. To provide incentives and thank participants, each will be provided a t-shirt advertising the event and earth day. | A table showing the types and amounts of waste cleaned up and where they were hauled to, two photographs of the event, and an event sign-in sheet. | B.6.7, B.6.2 | 2022-04-22 | 0.024038 | 8421 |  |  | 0 | 0
| 3.2 | [8 empty] | 0 | 0
| 3.3 | [8 empty] | 0 | 0
| 3.4 | [8 empty] | 0 | 0
| 3.5 | [8 empty] | 0 | 0
| 3.6 | [8 empty] | 0 | 0
| 3.7 | [8 empty] | 0 | 0
| 3.8 | [8 empty] | 0 | 0
| 3.9 | [8 empty] | 0 | 0
| 4 | Component #4: | [7 empty] | 0 | 0
| 4.1 | [8 empty] | 0 | 0
| 4.2 | [8 empty] | 0 | 0
| 4.3 | [8 empty] | 0 | 0
| 4.4 | [8 empty] | 0 | 0
| 4.5 | [8 empty] | 0 | 0
| 4.6 | [8 empty] | 0 | 0
| 4.7 | [8 empty] | 0 | 0
| 4.8 | [8 empty] | 0 | 0
| 4.9 | [8 empty] | 0 | 0
| 5 | Component #5: | [7 empty] | 0 | 0
| 5.1 | [8 empty] | 0 | 0
| 5.2 | [8 empty] | 0 | 0
| 5.3 | [8 empty] | 0 | 0
| 5.4 | [8 empty] | 0 | 0
| 5.5 | [8 empty] | 0 | 0
| 5.6 | [8 empty] | 0 | 0
| 5.7 | [8 empty] | 0 | 0
| 5.8 | [8 empty] | 0 | 0
| 5.9 | [8 empty] | 0 | 0
| 6 | Component #6: | [7 empty] | 0 | 0
| 6.1 | [8 empty] | 0 | 0
| 6.2 | [8 empty] | 0 | 0
| 6.3 | [8 empty] | 0 | 0
| 6.4 | [8 empty] | 0 | 0
| 6.5 | [8 empty] | 0 | 0
| 6.6 | [8 empty] | 0 | 0
| 6.7 | [8 empty] | 0 | 0
| 6.8 | [8 empty] | 0 | 0
| 6.9 | [8 empty] | 0 | 0
| 7 | Component #7: | [7 empty] | 0 | 0
| 7.1 | [8 empty] | 0 | 0
| 7.2 | [8 empty] | 0 | 0
| 7.3 | [8 empty] | 0 | 0
| 7.4 | [8 empty] | 0 | 0
| 7.5 | [8 empty] | 0 | 0
| 7.6 | [8 empty] | 0 | 0
| 7.7 | [8 empty] | 0 | 0
| 7.8 | [8 empty] | 0 | 0
| 7.9 | [8 empty] | 0 | 0
| 8 | Component #8: | [7 empty] | 0 | 0
| 8.1 | [8 empty] | 0 | 0
| 8.2 | [8 empty] | 0 | 0
| 8.3 | [8 empty] | 0 | 0
| 8.4 | [8 empty] | 0 | 0
| 8.5 | [8 empty] | 0 | 0
| 8.6 | [8 empty] | 0 | 0
| 8.7 | [8 empty] | 0 | 0
| 8.8 | [8 empty] | 0 | 0
| 8.9 | [8 empty] | 0 | 0
| 9 | Component #9: | [7 empty] | #REF! | #REF!
| 9.1 | [8 empty] | 0 | 0
| 9.2 | [8 empty] | 0 | 0
| 9.3 | [8 empty] | 0 | 0
| 9.4 | [8 empty] | 0 | 0
| 9.5 | [8 empty] | 0 | 0
| 9.6 | [8 empty] | 0 | 0
| 9.7 | [8 empty] | 0 | 0
| 9.8 | [8 empty] | 0 | 0
| 9.9 | [8 empty] | 0 | 0
|  | Workplan Totals |  |  |  | 0.2764 | 48257 |  |  | 0 | 0

## FY22 Cost Estimator
` | This is a partial GAP work plan example for illustrative purposes only. Grantees should develop work plans in alignment with the GAP statute, GAP Guidance and their own ETEPs. Use of this example does not guarantee approval or funding amounts.
|  | Common Autofill Data | [5 empty] | weekly to Yearly hrs
|  | Position | Salary | Hourly | IDC | Fringe |  | Hrs/week | Hrs/year
|  | Director | 68827.2 | 33.09 | 0.4313 | 0.26 |  | 4 | 208
|  | Manager | 57075.2 | 27.44 | 0.4313 | 0.3
|  | Assistant | 41600 | 20 | 0.4313 | 0.21
# | Component Titles & Commitments | Dir hrs. | Dir rate | Dir fringe | Mgr. hrs. | Mg rate | Mgr. fringe | Asst. hrs. | Asst. rate | Asst. fringe | Total Personnel | Travel (auto calc from bdgt) | Supplies (auto calc from bdgt | Other (auto calc from bdgt) | Indirect | Contract (no IDC) (auto calc) | Eqpmnt (no IDC) (auto calc) | Cmpnnt Cost | Cmpnnt FTE
1 | Administration of Environmental Office: | [16 empty] | 25654 | 0.1947
1.1 | The Director and Manager will administer general aspects of the GAP Grant, which will include but may not be limited to the following: answering phone calls, responding to emails, filing, attending weekly staff meetings, ordering supplies and equipment, adhering to time-keeping processes, paying utility bills, etc. Staff meetings will be held Mondays 8:30 - 9:30 AM. | 40 | 1324 | 344 | 100 | 2744 | 823 | 0 | 0 | 0 | 5235 | 0 | 864 | 1980 | 3484 | 0 | 0 | 11563 | 0.067308
1.2 | The Manager will prepare quarterly progress reports, submit them to the Director for review and submit final reports to US EPA by: Jan 30, Apr 28, Jul 31, and Oct 31. The Tribe will conduct a Joint Evaluation with US EPA GAP Project Officer. Evaluation elements are: 1. A discussion of accomplishments as measured against workplan commitments. 2. A discussion of cumulative effectiveness of the workplan performed under all workplan components. 3. A discussion of existing and potential problem areas. 4. Schedule discussions (4) with our Project Officer within two weeks of submitting progress reports. The Tribe will review a draft annual report prepared by US EPA and will discuss progress under the grant with US EPA prior to finalization of report. 5. Tribe will submit final evaluation reports to US EPA. | 30 | 993 | 258 | 60 | 1646 | 494 | 0 | 0 | 0 | 3391 | 0 | 0 | 0 | 1463 | 0 | 0 | 4854 | 0.043269
1.3 | The Director and Manager will work with the Tribal Accountant 2 times a month to review general ledgers, compare actual expenditures to projected expenditures, determine whether budget modifications are necessary, etc. The Manager will track all expenditures in a cuff-account spreadsheet and compare cuff-account data with the Tribe's offical ledger to help ensure charges to the GAP grant are correct. | 12 | 397 | 103 | 60 | 1646 | 494 | 0 | 0 | 0 | 2640 | 0 | 0 | 0 | 1139 | 0 | 0 | 3779 | 0.034615
1.4 | The Director and Manager will develop a calendar of upcoming training and events. The NRD and REPA Manager will share a Google Calender of trainings and events. This will help the program run effectively and efficiently and keep the program on track with workplan commitments and deliverables. | 10 | 331 | 86 | 20 | 549 | 165 | 0 | 0 | 0 | 1131 | 0 | 0 | 0 | 488 | 0 | 0 | 1619 | 0.014423
1.5 | The Director and Manager will attend monthly Council meetings on the 2nd Wednesday of each month to inform them of grant progress and environmental issues, and to seek approval of grant budgets, work plans, proposals, applications, purchases, travel, consultation correspondence, etc. | 12 | 397 | 103 | 30 | 823 | 247 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | 677 | 0 | 0 | 2247 | 0.020192
1.6 | The Manager and Director will continue to store and manage environmental and grant documents on the Triba/EPA OneDrive. They will update contacts information and email lists on as additional contacts are developed. | 1 | 33 | 9 | 30 | 823 | 247 | 0 | 0 | 0 | 1112 | 0 | 0 | 0 | 480 | 0 | 0 | 1592 | 0.014904
2 | Travel and Training | [16 empty] | 14182 | 0.0577
2.1 | The Manager and Director will drive (one vehicle) to San Francisco to attend the 2021 Annual tribal/EPA Conference and companion RTOC meeting in October. | 40 | 1324 | 344 | 40 | 1098 | 329 | 0 | 0 | 0 | 3095 | 4409 | 0 |  | 3236 | 0 | 0 | 10740 | 0.038462
2.2 | The Manager will fly to Reno to attend the 2021 Spring RTOC meeting, which is slated for 03/15/2022. |  | 0 | 0 | 40 | 1098 | 329 | 0 | 0 | 0 | 1427 | 978 | 0 | 0 | 1037 | 0 | 0 | 3442 | 0.019231
3 | Outreach and Education | [16 empty] | 8421 | 0.024
3.1 | Staff will plan, conduct and follow-up on one Rancheria cleanup day to celebrate earth day and improve awareness of solid waste issues and solutions. Cleanup activities will be distributed based on the age and physical condtion of participants. Children, elders and other physically compromised individuals will not be exposed to any heavy lifting or unsafe terrain. The goals of the event are to make people aware of illegal dumping and related environmental consequences, demonstrate how individuals can recycle and divert materials from their waste streams, and encourage people to recycle more and refrain from illegal dumping. Staff will develop a safety plan and conduct a safety meeting prior to participants starting the cleanup. All participants will be issued personal protective equipment such as gloves, goggles, hard hats, and face masks. To provide incentives and thank participants, each will be provided a t-shirt advertising the event and earth day. | 16 | 529 | 138 | 24 | 659 | 198 | 10 | 200 | 52 | 1776 | 0 | 450 | 0 | 960 | 0 | 5235 | 8421 | 0.024038
3.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Comp 4
4.1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
4.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Comp 5
5.1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Comp 6
6.1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Comp 7
7.1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Comp 8
8.1 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.3 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.4 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.5 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| TOTALS | 161 | 5328 | 1385 | 404 | 11086 | 3326 | 10 | 200 | 52 | 21377 | 5387 | 1314 | 1980 | 12964 | 0 | 5235 | 48257 | 0.2764
\
[17 empty] | L/R QA | 48257
[17 empty] | 575 | 0.2764
[9 empty] | incurs indirect |  | 30058 | Total personnel + Travel + Supplies + Other
[7 empty] | total personnel | 16614
[5 empty] | holiday = 80 |  | fringe | 4763 |  | incurs indirect |  | 30058
[5 empty] | PTO = 216 |  | travel | 5387
[5 empty] | Total = 296 |  | equipment | 5235
[7 empty] | supplies | 1314
[7 empty] | contractual | 0
[7 empty] | construction | 0
[7 empty] | other | 1980
[7 empty] | indirect | 12964
[7 empty] | total | 48257

## FY22 Draft Budget Detail
This is a partial GAP budget example for illustrative purposes only.Use of this example does not guarantee approval or funding amounts.
Oak Flat Tribe FY 2022 GAP Budget; GA 99T59201-2; Year 3; Approved 07/15/2021
Personnel (wage) | Rate/hr | Hours | FTE | totals | Additional Detail
Environmental Director | 33.09 | 161 | 0.0774 | 5328
Environmental Manager | 27.44 | 404 | 0.1942 | 11086
Environmental Assistant | 20 | 10 | 0.0048 | 200
Total Personnel |  | 575 | 0.2764 | 16614
Fringe | variable |  |  | 4763 | See cost estimator; Rate is 26% for Director, 30% for Manager, and 21% for Assistant.
Travel | # People | Rate | # Days/other | totals | Detailed Description
EPA Annual Conference SF |  |  |  | 4409 | Manager and Director will be attending the 2021 Tribal/EPA Conference in San Francisco. Travel is for commitment 2.1
lodging | 2 | 300 | 5 | 3000
pov mileage | 1 | 0.58 | 670 | 389
hotel parking | 1 | 52 | 5 | 260
per diem | 2 | 76 | 5 | 760
Fall RTOC meeting Reno |  |  |  | 978 | Manager will be attending the Fall RTOC meeting in Reno tentatively scheduled in Mid-Novermber 2021. Travel is for commitment 2.2
Lodging | 3 nights @ 115/night * 1 person |  |  | 345
Airfare | round trip @ 345 * 1 person |  |  | 345
Airport Parking | 3 days @ 20/day * 1 veh. |  |  | 60
per diem | 3 days @ 76/day | day * 1 person |  | 228
Total Travel |  |  |  | 5387
Equipment | Unit | # | Price | totals
Haul Trailer | trailer | 1 | 5235 | 5235 | Related to commitment 3.1 Trailer to be used for cleanups, recycling, etc.
Total Equipment |  |  |  | 5235
Supplies | Unit | # | Price | totals
Office supplies (1.1) |  |  |  | 864 | Consumables such as copier/printer/plotter paper and ink, pens and pencils, thumb drives, face masks, hand sanitizer….
Field Supplies (3.1) |  |  |  | 306 | Field supplies necessary for commitment 3.1
| hard hats | 3 | 52 | 156
| face masks | 15 | 3 | 45
| gloves | 15 | 7 | 105
Outreach Supplies (3.1) | t-shirts | 12 | 12 | 144 | Earth day cleanup t-shirts for commitment 3.1 participants
Total Supplies |  |  |  | 1314
Contractual | Unit | # | Price | Total
0
|  | Total Contractual |  | 0
Construction | Unit | # | Price | Total
|  | Total Construction |  | 0
Other | Unit | # | Price | Total
Electricity | PP&L bill | 12 | 120 | 1440
Oak Flat Public Utility | Water bill | 12 | 45 | 540
Total Other |  |  |  | 1980 | Costs shown in commitment 1.1
Direct costs that incur indirect charges (excludes equipment and contractual) |  |  |  | 30058
Indirect Costs |  | rate | 43.13% | 12964 | Rate approved 11/01/2020; Covers 10/01/2020 - 09/30/2021
Direct cost that do not incur indirect charges (Equipment and Contractual) |  |  |  | 5235 |  | 48257 | This quality assurance # is F58+F59+F60 as shown on this sheet.
GRAND TOTAL |  |  |  | 48257 |  |  | It agrees with F60 which is pulled from the FY22 Cost Estimator Tab and
also agrees with H88 as shown on the FY22 Draft Workplan tab.
* WORKPLAN TOTAL ( MUST MATCH BUDGET EXACTLY) |  |  |  | 0 |  |  | Things seem OK. QA checks like this are recommended.
Key: | costs from FY22 Cost Estimator tab
costs from this FY22 Budget Detail tab

## FY22 Progress Report & EOY
|  |  |  | ^^ <<- Workplan (for reference) | [5 empty] | Separate quarterly reporting tabs>>^^ | ^^ <<-Cumulative Reporting Tab | [6 empty] | ^^ <<-1st Q | [6 empty] | <<-- 2nd Q | [6 empty] | <<-- 3rd Q | [6 empty] | ^^ <<--4th Q | [13 empty] | ^^ EOY JOINT EVALUATION ^^
| GENERAL ASSISTANCE PROGRAM |  |  | GENERAL ASSISTANCE PROGRAM | [6 empty] | GENERAL ASSISTANCE PROGRAM | [6 empty] | GENERAL ASSISTANCE PROGRAM | [6 empty] | GENERAL ASSISTANCE PROGRAM | [6 empty] | GENERAL ASSISTANCE PROGRAM | [7 empty] | GENERAL ASSISTANCE PROGRAM
| (TRIBE'S OFFICIAL NAME) |  |  | (TRIBE'S OFFICIAL NAME) | [6 empty] | (TRIBE'S OFFICIAL NAME) | [6 empty] | (TRIBE'S OFFICIAL NAME) | [6 empty] | (TRIBE'S OFFICIAL NAME) | [6 empty] | (TRIBE'S OFFICIAL NAME) | [7 empty] | (TRIBE'S NAME _GRANT #_Fiscal Year_Year #)
| Grant #_Fiscal Year_Year # (xx/xx/xxxx - xx/xx/xxxx) |  |  | Cumulative Progress Reporting (1-4) _ Grant #_Fiscal Year_ Year # (10/01/22 - 09/30/23) | [6 empty] | 1st Quarter Progress Reporting _ Grant #_Fiscal Year_ Year # (10/01/22 - 12/31/22) | [6 empty] | 2nd Quarter Progress Reporting _ Grant #_Fiscal Year_ Year #( 01/01/23 - 3/30/23) | [6 empty] | 3rd Quarter Progress Reporting _ Grant #_Fiscal Year_ Year # ( 4/01/23 - 06/31/22) | [6 empty] | 4th Quarter Progress Reporting _ Grant #_Fiscal Year_ Year # (07/01/22 - 09/31/23) | [7 empty] | Fiscal Year 2022 4th/ Final Report & End of Year Joint Evaluation _ Grant # _ Fiscal Year _ Year # (09/30/2021 - 20/01/2022)
Columns AW through BC is for tribes to fill out if they wish to quantify the value of work and (or deliverables) that were completed. Use only with Project Officer Assistance.
Title <<-- | # | FY22 GAP Workplan Activity Descriptions | Approved Deliverables | # | Summary of Work Accomplished Q1-Q4 | Supporting Documentation Submitted | Status Update | Est. Total % Complete | Questions & Comments | EPA Response | # | Summary of Work Accomplished Q1 | Supporting Documentation Submitted | Status Update | Est. Total % Complete | Questions & Comments | EPA Response | # | Summary of Work Accomplished Q2 | Supporting Documentation Submitted | Status Update | Est. Total % Complete | Questions & Comments | EPA Response | # | Summary of Work Accomplished Q3 | Supporting Documentation Submitted | Status Update | Est. Total % Complete | Questions & Comments | EPA Response | # | Summary of Work Accomplished Q4 | Supporting Documentation Submitted | Status Update | Est. Total % Complete | Questions & Comments | EPA Response |  | # | Summary of All Accomplishments | Summary of All Supporting Documentation Provided | Summary of All Unsupported Work | Proposed Final Status | Total Est. % Complete | Supported Costs from workplan estimates | Supported Costs from deliverables submitted | Actual Cost | Conclusion/Explanation | EPA % Complete | Final Approved Cost | Conclusion/Resolution
| 1 | Administration of Environmental Office: | Environmental Outcomes: Compliance with Tribal and EPA administrative requirements and internally coordinated initiatives to improve environmental conditions ETEP Priority: #8 Environmental Office Administration | 1 | Administration | [5 empty] | 1 | Administration | [5 empty] | 1 | [6 empty] | 1 | [6 empty] | 1 | [7 empty] | 1 |  |  |  |  | 41.67% | 10689.1667 | 12827 | 13000 |  | 35.83% | 9192.6833
| 1.1 | The Director and Manager will administer general aspects of the GAP Grant, which will include but may not be limited to the following: answering phone calls, responding to emails, filing, attending weekly staff meetings, ordering supplies and equipment, adhering to time-keeping processes, paying utility bills, etc. Staff meetings will be held Mondays 8:30 - 9:30 AM. | 4 samples of weekly staff meeting notes and sign in sheets | 1.1 | Q1: Weekly staff meeting took place on 11/11/2020. the following items were discussed: future GAP funding, current project environemntal program is working on, community clean up event, quarterly newsletter. Q2: Weekly staff meeting took place on 2/11/2021. The following items were discussed: GAP application submitted, current projects environmental program is working on, summer internship program development, quarterly newsletter, TAS process. Q3: Q4: | Q1: Sign in sheets submitted in the OneDrive Q2: Sign in sheets submitted in the OneDrive Q3: Q4: | On Track | 50% | Are the deliverables that were submitted acceptable? | Q1: Deliverables were acceptable. Q2: Sign - sheets did not coincide with sample weekly staff meeting notes, but that's alright. Q3: Q4: | 1.1 | ED held weekly staff meetings throughout quarter 1. EA created agenda for each meeting and first visual displays of workplan commitments, progress to date and action items for the week ahead. | 3 meeting agendas with notes submitted. 3 photos of ELMS visual displays were submitted via email to GAP P.O. on 1/31/2021 | On Track (25%) | 25% | Are the deliverables that were submitted acceptable? | Deliverables were received and are of high quality. On track 25% confirmed. | 1.1 | ED held weekly staff meetings throughout quarter 1. EA created agenda for each meeting and first visual displays of workplan commitments, progress to date and action items for the week ahead. | 3 meeting agendas with notes submitted. 3 photos of ELMS visual displays were submitted via email to GAP P.O. on 1/31/2021 | On Track (50%) | 50% | None | Sign - sheets did not coincide with sample weekly staff meeting notes, but that's alright. | 1.1 | [6 empty] | 1.1 | [7 empty] | 1.1 |  |  |  |  | 50% | 5781.5 | 5781.5 |  |  | 50% | 5781.5
| 1.2 | The Manager will prepare quarterly progress reports, submit them to the Director for review and submit final reports to US EPA by: Jan 30, Apr 28, Jul 31, and Oct 31. The Tribe will conduct a Joint Evaluation with US EPA GAP Project Officer. Evaluation elements are: 1. A discussion of accomplishments as measured against workplan commitments. 2. A discussion of cumulative effectiveness of the workplan performed under all workplan components. 3. A discussion of existing and potential problem areas. 4. Schedule discussions (4) with our Project Officer within two weeks of submitting progress reports. The Tribe will review a draft annual report prepared by US EPA and will discuss progress under the grant with US EPA prior to finalization of report. 5. Tribe will submit final evaluation reports to US EPA. | 4 Quarterly Reports | 1.2 | Q1: Quarterly report submitted on 01/30/2021. Provided a summary for each commtiment in this current work plan. Q2: Quarterly report submitted on 04/30/2021. Provided a summary for each commtiment in this current work plan. Q3: Q4: | Q1: First quarterly report submitted in the OneDrive Q2: Second quarterly report submitted in the OneDrive Q3: Q4: | On Track | 50% | None | Q1: Report received Q2: Report received Q3: Q4: | 1.2 | ED and EA completed 3 monthly reports and submitted to council before council meetings. | 3 monthly reports were submitted to PO via email on 1/31/2021. | On Track (25%) | 25% | None | Deliverables were received. On track 25% confirmed. | 1.2 | ED and EA completed 3 monthly reports and submitted to council before council meetings. | 3 monthly reports were submitted to PO via email on 1/31/2021. | On Track (50%) | 50% | None | Report received | 1.2 | [6 empty] | 1.2 | [7 empty] | 1.2 |  |  |  |  | 50% | 2427 | 2427 |  |  | 50% | 2427
| 1.3 | The Director and Manager will work with the Tribal Accountant 2 times a month to review general ledgers, compare actual expenditures to projected expenditures, determine whether budget modifications are necessary, etc. The Manager will track all expenditures in a cuff-account spreadsheet and compare cuff-account data with the Tribe's offical ledger to help ensure charges to the GAP grant are correct. | 4 line item expenditure reports will be submitted along with EPA progress reports quarterly. | 1.3 | Q1: Expenditure reports for the months of Oct, Nov & Dec 2020 provided. Q2: Expenditure reports for the months of Jen, Feb & Mar 2021 provided. Q3: Q4: | Q1: Expenditure reports submitted in the OneDrive Q2: Expenditure reports submitted in the OneDrive Q3: Q4: | On Track | 50% | None | Q1: Located expenditure report Q2: Located expenditure report Q3: Q4: | 1.3 | Expenditure reports for the months of Oct, Nov & Dec 2020 provided. | Expenditure reports submitted in the OneDrive | On Track (25%) | 25% | None | Located expenditure report | 1.3 | Expenditure reports for the months of Jen, Feb & Mar 2021 provided. | Expenditure reports submitted in the OneDrive | On Track (50%) | 50% | None | Located expenditure report | 1.3 | [6 empty] | 1.3 | [7 empty] | 1.3 |  |  |  |  | 50% | 1889.5 | 1889.5 |  |  | 50% | 1889.5
| 1.4 | The Director and Manager will develop a calendar of upcoming training and events. The NRD and REPA Manager will share a Google Calender of trainings and events. This will help the program run effectively and efficiently and keep the program on track with workplan commitments and deliverables. | 4 samples of monthly calendars | 1.4 | Q1: No work just yet Q2: No work just yet Q3: Q4: | Q1: Nothing yet Q2: Nothing yet Q3: Q4: | Behind Schedule | 0% | Plan to develop this further in the next two quarters. | Q1: Sounds good. Q2: Should we consider modifying this commitment? Q3: Q4: | 1.4 | No work just yet | Nothing yet. | Behind Schedule |  | None | Sounds good | 1.4 | No work just yet | Nothing yet. | Behind Schedule |  | Plan to develop this further in the next two quarters. | Should we consider modifying this commitment? | 1.4 | [6 empty] | 1.4 | [7 empty] | 1.4 |  |  |  |  | 0% | 0 | 809.5 |  |  | 0% | 0
| 1.5 | The Director and Manager will attend monthly Council meetings on the 2nd Wednesday of each month to inform them of grant progress and environmental issues, and to seek approval of grant budgets, work plans, proposals, applications, purchases, travel, consultation correspondence, etc. | 3 monthly sign-in sheets and meeting notes | 1.5 | Q1: Submitted monthly sign in sheets and notes for Oct and Dec. The November meeting was canacelled. Q2: Submitted monthly sign in sheets and notes for Feb and March. The January meeting was canacelled. Q3: Q4: | Q1: Submitted monthly sign in sheets and notes for Oct and Dec in the OneDrive. Q2: Submitted monthly sign in sheets and notes for Feb and Mar in the OneDrive. Q3: Q4: | On Track | 50% | None | Q1: Sign in sheets and notes received. Q2: Sign in sheets and notes received. Q3: Q4: | 1.5 | Submitted monthly sign in sheets and notes for Oct and Dec. The November meeting was canacelled. | Submitted monthly sign in sheets and notes for Oct and Dec in the OneDrive. | On Track (25%) | 25% | None | Sign in sheets and notes received. | 1.5 | Submitted monthly sign in sheets and notes for Feb and March. The January meeting was canacelled. | Submitted monthly sign in sheets and notes for Feb and Mar in the OneDrive. | On Track (50%) | 50% | None | Sign in sheets and notes received. | 1.5 | [6 empty] | 1.5 | [7 empty] | 1.5 |  |  |  |  | 50% | 1123.5 | 1123.5 |  |  | 40% | 898.8
| 1.6 | The Manager and Director will continue to store and manage environmental and grant documents on the Triba/EPA OneDrive. They will update contacts information and email lists on as additional contacts are developed. | A copy of the contact list and two screen shots of OneDrive directories showing grants and directory structures. | 1.6 | Q1: Nothing yet Q2: Working on the contact list and devloping the OneDrive directories. Q3: Q4: | Q1: Nothing yet Q2: Screen shot of OneDrive directory being developed has been uploaded to the OneDrive file PO shared. Q3: Q4: | On Track | 50% | None | Q1: Thanks for the update. Q2: Located the screen shot of the OneDrive. During our quarterly review call can you explain the thought process behind what you are doing? It looks rather unique. Q3: Q4: | 1.6 | No work just yet | Nothing yet. | On Track (25%) |  | None | Thank you for the update | 1.6 | Working on the contact list and devloping the OneDrive directories. | Screen shot of OneDrive directory being developed has been uploaded to the OneDrive file PO shared. | On Track (50%) | 50% | None | Located the screen shot of the OneDrive. During our quarterly review call can you explain the thought process behind what you are doing? It looks rather unique. | 1.6 | [6 empty] | 1.6 | [7 empty] | 1.6 |  |  |  |  | 50% | 796 | 796 |  |  | 25% | 398
| 1.7 | #REF! | #REF! | 1.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 1.7 | [6 empty] | 1.7 | [6 empty] | 1.7 | [6 empty] | 1.7 | [7 empty] | 1.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 1.8 | #REF! | #REF! | 1.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 1.8 | [6 empty] | 1.8 | [6 empty] | 1.8 | [6 empty] | 1.8 | [7 empty] | 1.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 1.9 | #REF! | #REF! | 1.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 1.9 | [6 empty] | 1.9 | [6 empty] | 1.9 | [6 empty] | 1.9 | [7 empty] | 1.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 2 | Travel and Training | Increased knowledge of environmental issues & technical skills. | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [6 empty] | 2 | [7 empty] | 2 |  |  |  |  | 50% | 7091 | 5156.5 | 7000 |  | 50% | 7091
| 2.1 | The Manager and Director will drive (one vehicle) to San Francisco to attend the 2021 Annual tribal/EPA Conference and companion RTOC meeting in October. | Copies of any conference or RTOC presentations staff may develop and a summary of presentations or events attended. | 2.1 | Q1: Manager and Director attended the Annual Conference/RTOC on 10/25-10/28/2021. Q2: Acttivity completed in first quarter. Q3: Q4: | Q1: Two summaries for each staff member's attendance at the various workshops/trainings of the Annual Conference/RTOC were uploaded to the OneDrive. Q2: None Q3: Q4: | Completed (100%) | 100% | None | Q1: Summaries located on the OneDrive. Q2: Q3: Q4: | 2.1 | Manager and Director attended the Annual Conference/RTOC on 10/25-10/28/2021. | Two summaries for each staff member's attendance at the various workshops/trainings of the Annual Conference/RTOC were uploaded to the OneDrive. | Completed (100%) | 100% | None | Summaries located on the OneDrive. | 2.1 | Acttivity completed in first quarter. | None | Completed (100%) | 100% | None | None | 2.1 | [6 empty] | 2.1 | [7 empty] | 2.1 |  |  |  |  | 100% | 10740 | 4296 |  |  | 100% | 10740
| 2.2 | The Manager will fly to Reno to attend the 2021 Spring RTOC meeting, which is slated for 03/15/2022. | Copies of any meeting materials the Manager may develop and a summary of sessions attended if applicable. | 2.2 | Q1: No activity till the third quarter. Q2: No activity till the third quarter. Q3: Q4: | Q1: None Q2: None Q3: Q4: | On Track | 0% | None | Q1: None Q2: None Q3: Q4: | 2.2 | No activity till the third quarter. | None | On Track (25%) |  | None | None | 2.2 | No activity till the third quarter. | None | No Work Completed This Quarter |  | None | None | 2.2 | [6 empty] | 2.2 | [7 empty] | 2.2 |  |  |  |  | 0% | 0 | 860.5 |  |  | 0% | 0
| 2.3 | #REF! | #REF! | 2.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 2.3 | [6 empty] | 2.3 | [6 empty] | 2.3 | [6 empty] | 2.3 | [7 empty] | 2.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 2.4 | #REF! | #REF! | 2.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 2.4 | [6 empty] | 2.4 | [6 empty] | 2.4 | [6 empty] | 2.4 | [7 empty] | 2.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 2.5 | #REF! | #REF! | 2.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 2.5 | [6 empty] | 2.5 | [6 empty] | 2.5 | [6 empty] | 2.5 | [7 empty] | 2.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 2.6 | #REF! | #REF! | 2.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 2.6 | [6 empty] | 2.6 | [6 empty] | 2.6 | [6 empty] | 2.6 | [7 empty] | 2.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 2.7 | #REF! | #REF! | 2.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 2.7 | [6 empty] | 2.7 | [6 empty] | 2.7 | [6 empty] | 2.7 | [7 empty] | 2.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 2.8 | #REF! | #REF! | 2.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 2.8 | [6 empty] | 2.8 | [6 empty] | 2.8 | [6 empty] | 2.8 | [7 empty] | 2.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 2.9 | #REF! | #REF! | 2.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 2.9 | [6 empty] | 2.9 | [6 empty] | 2.9 | [6 empty] | 2.9 | [7 empty] | 2.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3 | Outreach and Education | 0 | 3 | [6 empty] | 3 | [6 empty] | 3 | [6 empty] | 3 | [6 empty] | 3 | [7 empty] | 3 |  |  |  |  | 10% | 842.1 | 0 | 240 |  | 0% | 0
| 3.1 | Staff will plan, conduct and follow-up on one Rancheria cleanup day to celebrate earth day and improve awareness of solid waste issues and solutions. Cleanup activities will be distributed based on the age and physical condtion of participants. Children, elders and other physically compromised individuals will not be exposed to any heavy lifting or unsafe terrain. The goals of the event are to make people aware of illegal dumping and related environmental consequences, demonstrate how individuals can recycle and divert materials from their waste streams, and encourage people to recycle more and refrain from illegal dumping. Staff will develop a safety plan and conduct a safety meeting prior to participants starting the cleanup. All participants will be issued personal protective equipment such as gloves, goggles, hard hats, and face masks. To provide incentives and thank participants, each will be provided a t-shirt advertising the event and earth day. | A table showing the types and amounts of waste cleaned up and where they were hauled to, two photographs of the event, and an event sign-in sheet. | 3.1 | Q1: No activity till the third quarter. Q2: No activity till the third quarter. We have had one planning meeting. Q3: Q4: | Q1: None Q2: Planning meetings notes have been submitted in teh OneDrive. Q3: Q4: | On Track | 10% | None | Q1: Thank you for the update Q2: Located the planning meeting notes in the OneDrive. Our Solid Waste Team is available if you have any questioned with the clean up event. Please let me know and I can set up a meeting with them. Q3: Q4: | 3.1 | No activity till the third quarter. | None | On Track (25%) |  | None | Thank you for the update | 3.1 | No activity till the third quarter. We have had one planning meeting. | Planning meetings notes have been submitted in teh OneDrive. | No Work Completed This Quarter | 10% | None | Located the planning meeting notes in the OneDrive. Our Solid Waste Team is available if you have any questioned with the clean up event. Please let me know and I can set up a meeting with them. | 3.1 | [6 empty] | 3.1 | [7 empty] | 3.1 |  |  |  |  | 10% | 842.1 | 0 |  |  | 0% | 0
| 3.2 | #REF! | #REF! | 3.2 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.2 | [6 empty] | 3.2 | [6 empty] | 3.2 | [6 empty] | 3.2 | [7 empty] | 3.2 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3.3 | #REF! | #REF! | 3.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.3 | [6 empty] | 3.3 | [6 empty] | 3.3 | [6 empty] | 3.3 | [7 empty] | 3.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3.4 | #REF! | #REF! | 3.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.4 | [6 empty] | 3.4 | [6 empty] | 3.4 | [6 empty] | 3.4 | [7 empty] | 3.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3.5 | #REF! | #REF! | 3.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.5 | [6 empty] | 3.5 | [6 empty] | 3.5 | [6 empty] | 3.5 | [7 empty] | 3.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3.6 | #REF! | #REF! | 3.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.6 | [6 empty] | 3.6 | [6 empty] | 3.6 | [6 empty] | 3.6 | [7 empty] | 3.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3.7 | #REF! | #REF! | 3.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.7 | [6 empty] | 3.7 | [6 empty] | 3.7 | [6 empty] | 3.7 | [7 empty] | 3.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3.8 | #REF! | #REF! | 3.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.8 | [6 empty] | 3.8 | [6 empty] | 3.8 | [6 empty] | 3.8 | [7 empty] | 3.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 3.9 | #REF! | #REF! | 3.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 3.9 | [6 empty] | 3.9 | [6 empty] | 3.9 | [6 empty] | 3.9 | [7 empty] | 3.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4 | #REF! | #REF! | 4 | [6 empty] | 4 | [6 empty] | 4 | [6 empty] | 4 | [6 empty] | 4 | [7 empty] | 4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.1 | #REF! | #REF! | 4.1 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.1 | [6 empty] | 4.1 | [6 empty] | 4.1 | [6 empty] | 4.1 | [7 empty] | 4.1 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.2 | #REF! | #REF! | 4.2 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.2 | [6 empty] | 4.2 | [6 empty] | 4.2 | [6 empty] | 4.2 | [7 empty] | 4.2 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.3 | #REF! | #REF! | 4.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.3 | [6 empty] | 4.3 | [6 empty] | 4.3 | [6 empty] | 4.3 | [7 empty] | 4.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.4 | #REF! | #REF! | 4.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.4 | [6 empty] | 4.4 | [6 empty] | 4.4 | [6 empty] | 4.4 | [7 empty] | 4.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.5 | #REF! | #REF! | 4.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.5 | [6 empty] | 4.5 | [6 empty] | 4.5 | [6 empty] | 4.5 | [7 empty] | 4.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.6 | #REF! | #REF! | 4.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.6 | [6 empty] | 4.6 | [6 empty] | 4.6 | [6 empty] | 4.6 | [7 empty] | 4.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.7 | #REF! | #REF! | 4.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.7 | [6 empty] | 4.7 | [6 empty] | 4.7 | [6 empty] | 4.7 | [7 empty] | 4.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.8 | #REF! | #REF! | 4.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.8 | [6 empty] | 4.8 | [6 empty] | 4.8 | [6 empty] | 4.8 | [7 empty] | 4.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 4.9 | #REF! | #REF! | 4.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 4.9 | [6 empty] | 4.9 | [6 empty] | 4.9 | [6 empty] | 4.9 | [7 empty] | 4.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5 | #REF! | #REF! | 5 | [6 empty] | 5 | [6 empty] | 5 | [6 empty] | 5 | [6 empty] | 5 | [7 empty] | 5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.1 | #REF! | #REF! | 5.1 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.1 | [6 empty] | 5.1 | [6 empty] | 5.1 | [6 empty] | 5.1 | [7 empty] | 5.1 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.2 | #REF! | #REF! | 5.2 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.2 | [6 empty] | 5.2 | [6 empty] | 5.2 | [6 empty] | 5.2 | [7 empty] | 5.2 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.3 | #REF! | #REF! | 5.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.3 | [6 empty] | 5.3 | [6 empty] | 5.3 | [6 empty] | 5.3 | [7 empty] | 5.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.4 | #REF! | #REF! | 5.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.4 | [6 empty] | 5.4 | [6 empty] | 5.4 | [6 empty] | 5.4 | [7 empty] | 5.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.5 | #REF! | #REF! | 5.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.5 | [6 empty] | 5.5 | [6 empty] | 5.5 | [6 empty] | 5.5 | [7 empty] | 5.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.6 | #REF! | #REF! | 5.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.6 | [6 empty] | 5.6 | [6 empty] | 5.6 | [6 empty] | 5.6 | [7 empty] | 5.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.7 | #REF! | #REF! | 5.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.7 | [6 empty] | 5.7 | [6 empty] | 5.7 | [6 empty] | 5.7 | [7 empty] | 5.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.8 | #REF! | #REF! | 5.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.8 | [6 empty] | 5.8 | [6 empty] | 5.8 | [6 empty] | 5.8 | [7 empty] | 5.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 5.9 | #REF! | #REF! | 5.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 5.9 | [6 empty] | 5.9 | [6 empty] | 5.9 | [6 empty] | 5.9 | [7 empty] | 5.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6 | #REF! | #REF! | 6 | [6 empty] | 6 | [6 empty] | 6 | [6 empty] | 6 | [6 empty] | 6 | [7 empty] | 6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.1 | #REF! | #REF! | 6.1 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.1 | [6 empty] | 6.1 | [6 empty] | 6.1 | [6 empty] | 6.1 | [7 empty] | 6.1 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.2 | #REF! | #REF! | 6.2 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.2 | [6 empty] | 6.2 | [6 empty] | 6.2 | [6 empty] | 6.2 | [7 empty] | 6.2 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.3 | #REF! | #REF! | 6.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.3 | [6 empty] | 6.3 | [6 empty] | 6.3 | [6 empty] | 6.3 | [7 empty] | 6.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.4 | #REF! | #REF! | 6.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.4 | [6 empty] | 6.4 | [6 empty] | 6.4 | [6 empty] | 6.4 | [7 empty] | 6.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.5 | #REF! | #REF! | 6.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.5 | [6 empty] | 6.5 | [6 empty] | 6.5 | [6 empty] | 6.5 | [7 empty] | 6.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.6 | #REF! | #REF! | 6.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.6 | [6 empty] | 6.6 | [6 empty] | 6.6 | [6 empty] | 6.6 | [7 empty] | 6.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.7 | #REF! | #REF! | 6.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.7 | [6 empty] | 6.7 | [6 empty] | 6.7 | [6 empty] | 6.7 | [7 empty] | 6.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.8 | #REF! | #REF! | 6.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.8 | [6 empty] | 6.8 | [6 empty] | 6.8 | [6 empty] | 6.8 | [7 empty] | 6.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 6.9 | #REF! | #REF! | 6.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 6.9 | [6 empty] | 6.9 | [6 empty] | 6.9 | [6 empty] | 6.9 | [7 empty] | 6.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7 | #REF! | #REF! | 7 | [6 empty] | 7 | [6 empty] | 7 | [6 empty] | 7 | [6 empty] | 7 | [7 empty] | 7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.1 | #REF! | #REF! | 7.1 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.1 | [6 empty] | 7.1 | [6 empty] | 7.1 | [6 empty] | 7.1 | [7 empty] | 7.1 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.2 | #REF! | #REF! | 7.2 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.2 | [6 empty] | 7.2 | [6 empty] | 7.2 | [6 empty] | 7.2 | [7 empty] | 7.2 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.3 | #REF! | #REF! | 7.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.3 | [6 empty] | 7.3 | [6 empty] | 7.3 | [6 empty] | 7.3 | [7 empty] | 7.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.4 | #REF! | #REF! | 7.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.4 | [6 empty] | 7.4 | [6 empty] | 7.4 | [6 empty] | 7.4 | [7 empty] | 7.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.5 | #REF! | #REF! | 7.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.5 | [6 empty] | 7.5 | [6 empty] | 7.5 | [6 empty] | 7.5 | [7 empty] | 7.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.6 | #REF! | #REF! | 7.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.6 | [6 empty] | 7.6 | [6 empty] | 7.6 | [6 empty] | 7.6 | [7 empty] | 7.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.7 | #REF! | #REF! | 7.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.7 | [6 empty] | 7.7 | [6 empty] | 7.7 | [6 empty] | 7.7 | [7 empty] | 7.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.8 | #REF! | #REF! | 7.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.8 | [6 empty] | 7.8 | [6 empty] | 7.8 | [6 empty] | 7.8 | [7 empty] | 7.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 7.9 | #REF! | #REF! | 7.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 7.9 | [6 empty] | 7.9 | [6 empty] | 7.9 | [6 empty] | 7.9 | [7 empty] | 7.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8 | #REF! | #REF! | 8 | [6 empty] | 8 | [6 empty] | 8 | [6 empty] | 8 | [6 empty] | 8 | [7 empty] | 8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.1 | #REF! | #REF! | 8.1 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.1 | [6 empty] | 8.1 | [6 empty] | 8.1 | [6 empty] | 8.1 | [7 empty] | 8.1 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.2 | #REF! | #REF! | 8.2 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.2 | [6 empty] | 8.2 | [6 empty] | 8.2 | [6 empty] | 8.2 | [7 empty] | 8.2 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.3 | #REF! | #REF! | 8.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.3 | [6 empty] | 8.3 | [6 empty] | 8.3 | [6 empty] | 8.3 | [7 empty] | 8.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.4 | #REF! | #REF! | 8.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.4 | [6 empty] | 8.4 | [6 empty] | 8.4 | [6 empty] | 8.4 | [7 empty] | 8.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.5 | #REF! | #REF! | 8.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.5 | [6 empty] | 8.5 | [6 empty] | 8.5 | [6 empty] | 8.5 | [7 empty] | 8.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.6 | #REF! | #REF! | 8.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.6 | [6 empty] | 8.6 | [6 empty] | 8.6 | [6 empty] | 8.6 | [7 empty] | 8.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.7 | #REF! | #REF! | 8.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.7 | [6 empty] | 8.7 | [6 empty] | 8.7 | [6 empty] | 8.7 | [7 empty] | 8.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.8 | #REF! | #REF! | 8.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.8 | [6 empty] | 8.8 | [6 empty] | 8.8 | [6 empty] | 8.8 | [7 empty] | 8.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 8.9 | #REF! | #REF! | 8.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 8.9 | [6 empty] | 8.9 | [6 empty] | 8.9 | [6 empty] | 8.9 | [7 empty] | 8.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9 | #REF! | #REF! | 9 | [6 empty] | 9 | [6 empty] | 9 | [6 empty] | 9 | [6 empty] | 9 | [7 empty] | 9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.1 | #REF! | #REF! | 9.1 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.1 | [6 empty] | 9.1 | [6 empty] | 9.1 | [6 empty] | 9.1 | [7 empty] | 9.1 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.2 | #REF! | #REF! | 9.2 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.2 | [6 empty] | 9.2 | [6 empty] | 9.2 | [6 empty] | 9.2 | [7 empty] | 9.2 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.3 | #REF! | #REF! | 9.3 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.3 | [6 empty] | 9.3 | [6 empty] | 9.3 | [6 empty] | 9.3 | [7 empty] | 9.3 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.4 | #REF! | #REF! | 9.4 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.4 | [6 empty] | 9.4 | [6 empty] | 9.4 | [6 empty] | 9.4 | [7 empty] | 9.4 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.5 | #REF! | #REF! | 9.5 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.5 | [6 empty] | 9.5 | [6 empty] | 9.5 | [6 empty] | 9.5 | [7 empty] | 9.5 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.6 | #REF! | #REF! | 9.6 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.6 | [6 empty] | 9.6 | [6 empty] | 9.6 | [6 empty] | 9.6 | [7 empty] | 9.6 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.7 | #REF! | #REF! | 9.7 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.7 | [6 empty] | 9.7 | [6 empty] | 9.7 | [6 empty] | 9.7 | [7 empty] | 9.7 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.8 | #REF! | #REF! | 9.8 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.8 | [6 empty] | 9.8 | [6 empty] | 9.8 | [6 empty] | 9.8 | [7 empty] | 9.8 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
| 9.9 | #REF! | #REF! | 9.9 | Q1: Q2: Q3: Q4: | Q1: Q2: Q3: Q4: |  |  |  | Q1: Q2: Q3: Q4: | 9.9 | [6 empty] | 9.9 | [6 empty] | 9.9 | [6 empty] | 9.9 | [7 empty] | 9.9 |  |  |  |  | 0% | #REF! | #REF! |  |  | #REF! | #REF!
|  | Workplan Totals | 0 | [11 empty] | 20% | [13 empty] | 50% | [6 empty] | 50% |  |  |  |  | Totals at Component level |  |  |  |  | 18622.2667 | 17983.5 | 20240 |  |  | 16283.6833 | Component (Pick one)
[41 empty] | Total at Commitment level |  |  |  |  | 23599.6 | 17983.5 |  |  |  | 22134.8 | Commitment (Pick one)
[40 empty] | FY2022 EOY Financial Summary |  | Totals | FY2022 Project Officer Summary | [5 empty] | Major Deliverables
[40 empty] | Award Amount |  | 48257 | [6 empty] | ETEP | Approved in FY17 (exp. FY21)
[40 empty] | Past Carryover Approved |  | n/a | [6 empty] | ISWMP | Being updated in FY20
[40 empty] | Total Funding Available |  | 48257 | [6 empty] | CWA TAS | Awaiting approval
[40 empty] | Sum of Commitments/ Workplan Total |  | 48257
Expenditures per FFR
[40 empty] | Supported Costs |  | 16283.6833
Funds remaining per FFR (Unobligated Balance)
Unsupported Costs
Funds Spent are Commensurate with Work Performed (Yes/No)
Resolution Required (Yes/No)
Carryforward Approved
(TRIBE'S NAME _GRANT #_Fiscal Year_Year #)
FY22-FY26 Grant Period Financial Overview / Close-out Report Table
[40 empty] | Grant Sequence |  | Funding Period | Award Amount | Expended Amount* | Comments
[40 empty] | GA- |  | 10/1/2022-9/30/2023 | 48602
GA-
GA-
GA-
GA-
[42 empty] | Total: | 48602 | 0
[42 empty] | Balance |  | 48602
*Expended amount as stated on an interim or final FFR
i

## Cumulative Qtl Report
(TRIBE'S NAME )
Cumulative Progress Reporting (1-4)_ Grant #_Fiscal Year_ Year # (10/01/22 - 09/30/23)
# | Approved Commitments | Approved Deliverables | Summary of Work Performed | Actual Deliverables (List deliverables provide (where & when), e.g., email (0/15/22), SharePoint, etc.) | Check if work was completed on the commitment this quarter |  |  |  | Status (complete, in progress, partially complete, not yet started/incomplete) | Estimated % Complete | Approved Costs | Estimated Supported Costs | Quarterly Report Comments
[5 empty] | Q1 | Q2 | Q3 | Q4
1 | Administration of Environmental Office: | Environmental Outcomes: Compliance with Tribal and EPA administrative requirements and internally coordinated initiatives to improve environmental conditions ETEP Priority: #8 Environmental Office Administration | [7 empty] | 41.67% | 25654 | 10689.1667
1.1 | The Director and Manager will administer general aspects of the GAP Grant, which will include but may not be limited to the following: answering phone calls, responding to emails, filing, attending weekly staff meetings, ordering supplies and equipment, adhering to time-keeping processes, paying utility bills, etc. Staff meetings will be held Mondays 8:30 - 9:30 AM. | 4 samples of weekly staff meeting notes and sign in sheets | Q1: Weekly staff meeting took place on 11/11/2020. the following items were discussed: future GAP funding, current project environemntal program is working on, community clean up event, quarterly newsletter. Q2: Weekly staff meeting took place on 2/11/2021. The following items were discussed: GAP application submitted, current projects environmental program is working on, summer internship program development, quarterly newsletter, TAS process. Q3: Q4: | Q1: Sign in sheets submitted in the OneDrive Q2: Sign in sheets submitted in the OneDrive Q3: Q4: | X | X |  |  | In Progress | 50% | 11563 | 5781.5
1.2 | The Manager will prepare quarterly progress reports, submit them to the Director for review and submit final reports to US EPA by: Jan 30, Apr 28, Jul 31, and Oct 31. The Tribe will conduct a Joint Evaluation with US EPA GAP Project Officer. Evaluation elements are: 1. A discussion of accomplishments as measured against workplan commitments. 2. A discussion of cumulative effectiveness of the workplan performed under all workplan components. 3. A discussion of existing and potential problem areas. 4. Schedule discussions (4) with our Project Officer within two weeks of submitting progress reports. The Tribe will review a draft annual report prepared by US EPA and will discuss progress under the grant with US EPA prior to finalization of report. 5. Tribe will submit final evaluation reports to US EPA. | 4 Quarterly Reports | Q1: Quarterly report submitted on 01/30/2021. Provided a summary for each commtiment in this current work plan. Q2: Quarterly report submitted on 04/30/2021. Provided a summary for each commtiment in this current work plan. Q3: Q4: | Q1: First quarterly report submitted in the OneDrive Q2: Second quarterly report submitted in the OneDrive Q3: Q4: | X | X |  |  | In Progress | 50% | 4854 | 2427
1.3 | The Director and Manager will work with the Tribal Accountant 2 times a month to review general ledgers, compare actual expenditures to projected expenditures, determine whether budget modifications are necessary, etc. The Manager will track all expenditures in a cuff-account spreadsheet and compare cuff-account data with the Tribe's offical ledger to help ensure charges to the GAP grant are correct. | 4 line item expenditure reports will be submitted along with EPA progress reports quarterly. | Q1: Expenditure reports for the months of Oct, Nov & Dec 2020 provided. Q2: Expenditure reports for the months of Jen, Feb & Mar 2021 provided. Q3: Q4: | Q1: Expenditure reports submitted in the OneDrive Q2: Expenditure reports submitted in the OneDrive Q3: Q4: | X | X |  |  | In Progress | 50% | 3779 | 1889.5
1.4 | The Director and Manager will develop a calendar of upcoming training and events. The NRD and REPA Manager will share a Google Calender of trainings and events. This will help the program run effectively and efficiently and keep the program on track with workplan commitments and deliverables. | 4 samples of monthly calendars | Q1: No work just yet Q2: No work just yet Q3: Q4: | Q1: Nothing yet Q2: Nothing yet Q3: Q4: | - | - |  |  | Not Yet Started/Incomplete | 0% | 1619 | 0
1.5 | The Director and Manager will attend monthly Council meetings on the 2nd Wednesday of each month to inform them of grant progress and environmental issues, and to seek approval of grant budgets, work plans, proposals, applications, purchases, travel, consultation correspondence, etc. | 3 monthly sign-in sheets and meeting notes | Q1: Submitted monthly sign in sheets and notes for Oct and Dec. The November meeting was canacelled. Q2: Submitted monthly sign in sheets and notes for Feb and March. The January meeting was canacelled. Q3: Q4: | Q1: Submitted monthly sign in sheets and notes for Oct and Dec in the OneDrive. Q2: Submitted monthly sign in sheets and notes for Feb and Mar in the OneDrive. Q3: Q4: | X | X |  |  | In Progress | 50% | 2247 | 1123.5
1.6 | The Manager and Director will continue to store and manage environmental and grant documents on the Triba/EPA OneDrive. They will update contacts information and email lists on as additional contacts are developed. | A copy of the contact list and two screen shots of OneDrive directories showing grants and directory structures. | Q1: Nothing yet Q2: Working on the contact list and devloping the OneDrive directories. Q3: Q4: | Q1: Nothing yet Q2: Screen shot of OneDrive directory being developed has been uploaded to the OneDrive file PO shared. Q3: Q4: | - | X |  |  | In Progress | 50% | 1592 | 796
2 | Travel and Training | Increased knowledge of environmental issues & technical skills. | [7 empty] | 50% | 14182 | 7091
2.1 | The Manager and Director will drive (one vehicle) to San Francisco to attend the 2021 Annual tribal/EPA Conference and companion RTOC meeting in October. | Copies of any conference or RTOC presentations staff may develop and a summary of presentations or events attended. | Q1: Manager and Director attended the Annual Conference/RTOC on 10/25-10/28/2021. Q2: Activity completed in first quarter. Q3: Q4: | Q1: Two summaries for each staff member's attendance at the various workshops/trainings of the Annual Conference/RTOC were uploaded to the OneDrive. Q2: None Q3: Q4: | X |  |  |  | Complete | 100% | 10740 | 10740
2.2 | The Manager will fly to Reno to attend the 2021 Spring RTOC meeting, which is slated for 03/15/2022. | Copies of any meeting materials the Manager may develop and a summary of sessions attended if applicable. | Q1: No activity till the third quarter. Q2: No activity till the third quarter. Q3: Q4: | Q1: Nothing yet Q2: Nothing yet Q3: Q4: | - | - |  |  | Not Yet Started/Incomplete | 0% | 3442 | 0
3 | Outreach and Education | 0 | [7 empty] | 10% | 8421 | 842.1
3.1 | Staff will plan, conduct and follow-up on one Rancheria cleanup day to celebrate earth day and improve awareness of solid waste issues and solutions. Cleanup activities will be distributed based on the age and physical condtion of participants. Children, elders and other physically compromised individuals will not be exposed to any heavy lifting or unsafe terrain. The goals of the event are to make people aware of illegal dumping and related environmental consequences, demonstrate how individuals can recycle and divert materials from their waste streams, and encourage people to recycle more and refrain from illegal dumping. Staff will develop a safety plan and conduct a safety meeting prior to participants starting the cleanup. All participants will be issued personal protective equipment such as gloves, goggles, hard hats, and face masks. To provide incentives and thank participants, each will be provided a t-shirt advertising the event and earth day. | A table showing the types and amounts of waste cleaned up and where they were hauled to, two photographs of the event, and an event sign-in sheet. | Q1: No activity till the third quarter. Q2: No activity till the third quarter. We have had one planning meeting. Q3: Q4: | Q1: None Q2: Planning meetings notes have been submitted in the OneDrive. Q3: Q4: | - | X |  |  | In Progress | 10% | 8421 | 842.1
FY 22 EOY Summary |  |  |  | Project Officer Summary
Award Amount |  | 48257
Approved Carryover |  | 0
Total Funding Approved |  | 48257
Expenditures per FFR
Estimated Supported Expenditures |  | 18622.2667
Funds remaining per FFR
Unsupported Expenditures

## Progress & EOY Simple
(TRIBE'S OFFICIAL NAME)
Grant #_Fiscal Year_Year # (xx/xx/xxxx - xx/xx/xxxx)
Quarterly Progress Reporting and EOY Joint Evaluation
# | Activity Descriptions | Approved Deliverables Submitted | Q1 | Q2 | Q3 | Q4 | Status | % Complete | Approved Amount | Justified Expenditures | Quarterly Report Comments
1 | Component #1: | [6 empty] | 41.67% | 25654 | 10689.1667
1.1 |  | Q1: Sign in sheets submitted in the OneDrive Q2: Sign in sheets submitted in the OneDrive Q3: Q4: | X | X |  |  | On track | 50% | 11563 | 5781.5
1.2 |  | Q1: First quarterly report submitted in the OneDrive Q2: Second quarterly report submitted in the OneDrive Q3: Q4: | X | X |  |  | On track | 50% | 4854 | 2427
1.3 |  | Q1: Expenditure reports submitted in the OneDrive Q2: Expenditure reports submitted in the OneDrive Q3: Q4: | X | X |  |  | On track | 50% | 3779 | 1889.5
1.4 |  | Q1: None Q2: None Q3: Q4: | - | - |  |  | Behind Schedule | 0% | 1619 | 0
1.5 |  | Q1: Submitted monthly sign in sheets and notes for Oct and Dec in the OneDrive. Q2: Submitted monthly sign in sheets and notes for Feb and Mar in the OneDrive. Q3: Q4: | X | X |  |  | On track | 50% | 2247 | 1123.5
1.6 |  | Q1: Nothing yet Q2: Screen shot of OneDrive directory being developed has been uploaded to the OneDrive file PO shared. Q3: Q4: | - | X |  |  | On track | 50% | 1592 | 796
1.7 | [8 empty] | 14182 | 0
1.8 | [8 empty] | 10740 | 0
1.9 | [8 empty] | 3442 | 0
2 | Component #2: | [6 empty] | 50% | 14182 | 7091
2.1 |  | Q1: Two summaries for each staff member's attendance at the various workshops/trainings of the Annual Conference/RTOC were uploaded to the OneDrive. Q2: None Q3: Q4: | X |  |  |  | Complete | 100% | 10740 | 10740
2.2 |  | Q1: None Q2: None Q3: Q4: | - | - |  |  | Not Yet | 0% | 3442 | 0
2.3 | [8 empty] | 0 | 0
2.4 | [8 empty] | 0 | 0
2.5 | [8 empty] | 0 | 0
2.6 | [8 empty] | 0 | 0
2.7 | [8 empty] | 0 | 0
2.8 | [8 empty] | 0 | 0
2.9 | [8 empty] | 0 | 0
3 | Component #3: | [6 empty] | 10% | 8421 | 842.1
3.1 |  | Q1: None Q2: Planning meetings notes have been submitted in the OneDrive. Q3: Q4: | - | X |  |  | On track | 10% | 8421 | 842.1
3.2
3.3
3.4
3.5
3.6
3.7
3.8
3.9
4 | Component #4:
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
5 | Component #5:
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
6 | Component #6:
6.1
6.2
6.3
6.4
6.5
6.6
6.7
6.8
6.9
7 | Component #7:
7.1
7.2
7.3
7.4
7.5
7.6
7.7
7.8
7.9
8 | Component #8:
8.1
8.2
8.3
8.4
8.5
8.6
8.7
8.8
8.9
9 | Component #9:
9.1
9.2
9.3
9.4
9.5
9.6
9.7
9.8
9.9
[10 empty] | 18622.2667 | Component Level
| Workplan Total | [8 empty] | 23599.6 | Commtiment Level
[7 empty] | FY 22 EOY Summary |  |  |  | Project Officer Summary
[7 empty] | Award Amount |  | 48257
[7 empty] | Approved Carryover |  | 0
[7 empty] | Total Funding Approved |  | 48257
Expenditures per FFR
[7 empty] | Supported Expenditures |  | 18622.2667
Funds remaining per FFR
Unsupported Expenditures

## Deliverable Status
Disclaimer: The estimated % complete generated by this tool weighs all deliverables within a commitment equally. As this does not reflect actual time spent or cost for each deliverable, the % complete is a rough estimate and serves as a starting point for a more nuanced conversation and thorough joint evaluation.
Comm. | Qty. | Deliverables | Q1 | Q2 | Q3 | Q4 | % Complete
1.1 | [6 empty] | 50%
| 4 | Sign in sheets | 1 | 1 |  |  | 50%
1.2 | [6 empty] | 50%
| 4 | Quarterly reports | 1 | 1 |  |  | 50%
1.3 | [6 empty] | 50%
| 4 | Quarterly expenditure reports | 1 | 1 |  |  | 50%
1.4 | [6 empty] | 0%
| 4 | Samples of monthly calendars | - | - |  |  | 0%
1.5 | [6 empty] | 40%
12 | 10 | Monthly sign in sheets | 2 | 2 |  |  | 40% | *Decreased amount of sign in sheets and notes because nto all meetings took place
12 | 10 | Monthly notes | 2 | 2 |  |  | 40%
1.6 | [6 empty] | 25%
| 1 | Contact list | - | - |  |  | 0%
| 2 | Screen shots of directory | - | 1 |  |  | 50%
2.1 | [6 empty] | 100%
| 2 | Summries of Annual Conference attended | 2 | - | - | - | 100%
2.2 | [6 empty] | 0%
| 1 | Summary of RTOC attended | - | - |  |  | 0%
3.1 | [6 empty] | 0%
| 1 | Table with amounts and types of waste collected | - | - |  |  | 0%
| 2 | Photos | - | - |  |  | 0%
| 1 | Sign in sheets | - | - |  |  | 0%