## Matrix
GitHub Revision Number | GitHub Commit Date | Code Note | Programmer Test Date | Programmer Comment # | WPC Test Complete Date | WPC Comment Number | CSRA Unit Test Completed | CSRA Comment # | Delivered to EPA | EPA Test (optional) | EPA Comment #
12e756b | 2016-12-09 | Task 6, DBMS, Draft 1 | 2016-12-09 | 1 | YES | 4 |  |  | ongoing
75a4d06 | 2016-12-15 | Task 4 & DBMS, Draft 2 | 2016-12-15 | 2 | YES | 5 |  |  | via github
59303b3 | 2017-01-04 | Task 6, DBMS, Draft 3 | 2016-01-04 | 3 | YES | 6 |  |  | ongoing
daab7b2 | 2017-01-10 | Task 2, Estuarine, Dr. 1 | 2017-01-10 | 7 | N/A test next commit (1/11) |  |  |  | via github
f6aa0f3 | 2017-01-10 | Quick Bug Fix Develop | 2017-01-10 | 8 | YES | 6 |  |  | ongoing
797a5ca | 2017-01-11 | Task 2: Estuarine, Dr.2 | 2017-01-11 | 9 | YES | 10 | 2017-01-13 | 11 | via github
4411c8b | 2017-01-19 | Task 2: Estuarine, Dr.3 | 2017-01-19 | 10 | YES | 10 |  |  | ongoing
75b96fa | 2017-01-30 | Task 5 ASCII I/O Draft 1 | 2017-01-30 | 12 | YES | 13 |  |  | via github
9145c7a | 2017-02-01 | Task 5 ASCII I/O Draft 2 | 2017-02-01 | 14 | YES | 15 |  |  | ongoing
a154b1f | 2017-02-16 | Task 5 Command Line | 2017-02-16 | 16 | 2017-02-22 | 17 |  |  | via github
9700da4 | 2017-02-27 | Task 5 Complete | 2017-02-27 | 18 | 2017-03-07 | 19 |  |  | via github
TBD | 2017-04-03 | AQUATOX 3.2 Release Candidate-- no known issues
Comment # | Comment:
1.) | JSC: Tested each database interface as coded, stepped through modified code in debug mode, tested deployment on multiple machines and Windows OS, no known issues at this point
2.) | Task 4 -- animal- and plant-specific Weibull Slope factors implemented for toxicity calculations. Fix of several issues Marco Propato found within Release 3.2, details on next sheet.
3.) | JSC: Fixed issues found within Release 3.2, details on next sheet. Tested fixes and issues appear to be resolved.
4.) | MP: Tested Sudies compatibility results between 3.1 and 3.2 versions and start testing new interface. Some bugs found in the forms but Studies result appear to be compatible with previous version results
5.) | MP: Tested GUI forms functionality. Some bugs identified.
6.) | MP: Tested the fixes made by JSC. No remaining issues. (site-database issues were due to a deployment problem of DB files different than those in GitHub commit.)
7.) | JSC: All 3.1 NME changes brought into 3.2. Tested loading and saving and running of 3.1, 3.1+, and 3.1 NME studies with no found issues.
8.) | Single line of code changed-- a bug was not allowing database edits to be saved back to the original SQLite database. Problem is now resolved.
9.) | JSC: Nearshore Marine Environment versions and documentation complete and ready for unit testing. Programmer testing found no additional issues.
10.) | MP: Five issues found as detailed on Verbose Issues List, next page. JSC: Resolved these issues in Commit of 1/19/2017
11.) | Tutorial test completed on January 13th, and some changes to the documentation were recommended. Results emailed in "Aquatox Tutorial Testing.xlsx"
12.) | Spot checked import and output of ASCII files with no known issues -- full test pending
13.) | MP: Loaded all studies, saved to text, re-loaded, checked parameters, checked model results. Found several issues that require resolution, see "verbose" page
14.) | JSC: Reproduced all problems reported by MP, resolved each of them. No additional known issues.
15.) | MP: Loaded all studies that had problems, saved to text, re-loaded, checked parameters, checked model results. Issues resolved in 2/1 commit.
16.) | JSC: Command Line options completed and documented and spot checked. No known issues pending Marco's testing.
17.) | MP: Batch automated test of all als and aps files. Excel output is very slow due to OLE automation issue-- CSV output is better choice. A few dialog popups pause command line. Minor text differences
18.) | Resolved all dialog popups in command-line mode; text differences are in interim calculations only, not a problem -- will document; no known issues; documentation completed.
19.) | A few minor issues were found in testing the merged-branch version as shown in the "Verbose Issues List" tab that follows. All issues were resolved

## Verbose Issues List
GitHub Revision Number | GitHub Commit Date | Tester | Resolved | Details
75a4d06 | 2016-12-15 | MP | yes, testing pending | Coral Res IA Sens.aps: Error when clicking output: "Cannot access tornado diagram excel file". Does not happen with 3.1 (JSC Initial Fix completed and testing, more testing required, middle line not drawn temporarily)
75a4d06 | 2016-12-15 | MP | yes | Lake Ontario PCBs: Sed Layers window not working (JSC Fixed, sed-layers database interface update was required)
75a4d06 | 2016-12-15 | MP | yes | When one scroll on the legend, the series name becomes red but there is no other change observed (JSC tested, new graphing component behavior -- but harmless)
75a4d06 | 2016-12-15 | MP | yes | Multi segment drop down window is difficult to read (blue color over black) (JSC Fixed)
75a4d06 | 2016-12-15 | MP | yes, workaround | Log scales have colored ticks (e.g. daphnia rates) (JSC Fixed -- workaround for now)
75a4d06 | 2016-12-15 | MP | yes, workaround | No y­axis units labels (JSC Fixed -- new graphing component behavior -- not working with editable fonts -- as a workaround axis units are visible but font temporarily not editable)
75a4d06 | 2016-12-15 | MP | yes | Sometimes legend labels appear as "SeriesN" but really no series there (in the old version there was a blank line separating graphs with different units) (JSC Fixed -- new component behavior, won't print space characters in legend that were used as a spacer, replaced with dashes)
75a4d06 | 2016-12-15 | MP | yes | ErrVal - always 0 in both versions (JSC Fixed, err.val. -- this is interface informational output only, and does not change model results -- display should have been normalized to relative error.)
75a4d06 | 2016-12-15 | MP | yes | Multi-segment run the run window does not specify which project is running in both versions (This also was an issue with 3.1 plus; JSC Fixed)
59303b3 | 2017-01-04 | MP | yes | The trophic-interactions matrix window was not working properly due to upgrade to Unicode components.
59303b3 | 2017-01-04 | MP | yes | Excel output now properly defaults to xls extension rather than xlsx.
59303b3 | 2017-01-04 | MP | yes | Fixed a bug when adding an age-class fish through the Wizard interface.
59303b3 | 2017-01-04 | MP | yes | Fixed floating point errors that could occur when using the "convert units" interface.
59303b3 | 2017-01-04 | MP | yes | Loading site and remineralization records from the database was not working properly. This has been fixed.
59303b3 | 2017-01-04 | MP | yes | Tornado diagrams lacked vertical line at center [JSC Fixed 1/4/2017]
59303b3 | 2017-01-04 | MP | yes | Congratulations? at the end of wizard can be removed / changed to something else. [JSC Reworded dated and imprecise dialog 1/4/2017]
59303b3 | 2017-01-04 | MP | yes, workaround | Site Library gives an error when scrolling to different site after pressing Grid Mode [JSC In progress -- SQL database problem. SQL error. Workaround in place at the moment.]
59303b3 | 2017-01-04 | MP | yes | When exiting Trophic Interactions editing from Animal database window, the database is saved whether cancel is later pressed or not. [JSC Fixed Interface Behavior, added clarifying message dialog. 1/4/2017]
797a5ca | 2017-01-11 | MP | yes | 1/17/17: Access error after modifying toolbar (adding/deleting items or adding lines) [JSC reproduced and fixed 1/17/2017]
797a5ca | 2017-01-11 | MP | yes | 1/16/17: Load DeGray Reservoir AR - Select a segment - Add Multi-Age Class Fish - Select Db - Invalid Pointer Operation - Access Violation - it stays open and uses CPU [JSC Fixed 1-17]
797a5ca | 2017-01-11 | MP | yes | 1/16/17 When trying to open other libraries (other table) and select another one that is not of the correct type - File format error -- [JSC significantly improve error messages showing a general error 1-17]
797a5ca | 2017-01-11 | MP | yes | 1/16/17 Does edit toolbar work? Cancel button is missing. Yes it works, needs better wording. Cancel button lower priority. [JSC Reworded 1-17]
797a5ca | 2017-01-11 | MP | yes | 1/13/2017 - Coralville Res IA Dieldrin.aps - Fish (welleye/largemouth bass especially but all ot them)) behavior is different [JSC Fixed 1-16]
75b96fa | 2017-01-30 | MP | yes | Blue Earth R.MN.aps; On execution of txt project “Run-Time Error”
75b96fa | 2017-01-30 | MP | yes | Cahaba R AL X2 TSS.aps “Collection Boundary Exceeded Error” when loading txt:
75b96fa | 2017-01-30 | MP | yes | Clear Lake CA Fluridone.aps “Text Read Name mismatch due to bad characters” when loading txt: -- FIXED
75b96fa | 2017-01-30 | MP | yes | East Fork Poplar Creek TN PCBs.aps; Run time error on execution of txt project FIXED
75b96fa | 2017-01-30 | MP | yes | Expr Stream Esfenval.aps -- Range check error also on aps version (it works on 3.2), JSC FIXED
75b96fa | 2017-01-30 | MP | yes | Farm Pond MO Esfenval.aps Error when loading txt FIXED
75b96fa | 2017-01-30 | MP | yes | Lower Boise R ID Seg_1-3 Diel.als Can save text but after I/O 104 when trying to reopen als JSC FIXED
9700da4 | 2017-03-07 | MP | yes | Load DeGray Reservoir AR - Select a segment - Add Multi-Age Class Fish - Press Older migration or YOY Migration - Access violation; JSC fixed 3-15-2017
9700da4 | 2017-03-07 | MP | yes | Wizard steps 9/10/11 windows disappear sometime; JSC fixed the issue of the disappearing window -- http://stackoverflow.com/questions/1639125/form-is-hidden-behind-other-forms-when-showmodal-is-called
9700da4 | 2017-03-07 | MP | yes | Multi-segment projects are in 3.95 version; JSC upgraded projects to latest version-- 3-15-2017
9700da4 | 2017-03-07 | MP | yes | Animal DB: MP Asked -- What is the difference when a square is checked with V ot fully blue? JSC “True” is checked, “false” is unchecked, blue is “no-data” interpreted as false, JSC replaced “no data” with “false” for clarity whenever possible.